## Features
Feature / Drop | Testing level |  | Main Tools | Framework | Tools
Registration | UI testing | Backend Testing | Java + Selenium + Api | Cucumber BDD | Jira-Xray /Git GitHub
Login Functionality | UI testing | Backend Testing | Java + Selenium + Api | Cucumber BDD | Jira-Xray /Git GitHub
Customer Functionalities | UI testing | Backend Testing | Java + Selenium + Api | Cucumber BDD | Jira-Xray /Git GitHub
Store Manager Functionalities | UI testing | Backend Testing | Java + Selenium + Api | Cucumber BDD | Jira-Xray /Git GitHub
Admin Functionalities | UI testing | Backend Testing | Java + Selenium + Api | Cucumber BDD | Jira-Xray /Git GitHub

## Product Backlog
User_Story_ID | Description | Acceptance Criteria | Priority | Validation | Story Points
US01 | Register an account as a new user. | 1. The user must be able to register with a valid Name, Email, and Password. | High | Validate registration with test cases for required fields and success message. Validate the registered user via API request as backend validation.
2. An error should be displayed if any required field is missing.
3. An error should be displayed if the email is in an invalid format.
4. An error should be displayed if the Name contains any character other than letters.
5. An error should be displayed if the Password's length is less than 6 characters.
6. An error should be displayed if the Confirm Password field does not match.
7. Registration should confirm the successful creation of the account.
US02 | Log in as a user to access the platform. | 1. The user must log in using valid Email and Password. | High | Validate login functionality with valid and invalid credentials. Validate login functionality via API request as backend validation.
2. An error message should appear for incorrect credentials.
3. A validation error should appear if the email is in an invalid format.
4. A validation error should appear if any required field is missing.
5. A successful login redirects to the dashboard.
US03 | Log out of the platform as a user. | 1. The user can click "Log out" from the dashboard. | Medium | Validate log-out flow and session termination. Validate log out functionality via API request as backend validation.
2. Logging out redirects the user to the login page.
3. The session must be securely terminated.
US04 | Browse products as a customer. | 1. Customer can see products on customer page. | High | Validate product browsing functionality. Validate the products you get via Selenium and API.
2. Products must load quickly and show Name, Price, Description, and Images
US05 | View product details as a customer. | 1. Clicking a product shows detailed information (Name, Price, Description, and Images). | Medium | Validate product detail page displays all required information. Validate the product you get via Selenium and API.
US06 | Add products to the cart as a customer. | 1. Clicking "Add to Cart" adds the product to the cart. | High | Validate cart updates after adding a product. Validate cart updates after adding a product via API.
2. A success notification is shown.
3. The cart count updates automatically.
US07 | Mark products as favorites as a customer. | 1. Clicking the heart icon saves the product as a favorite. | Medium | Validate heart icon functionality and favorite list page. Validate heart icon functionality and favorite list page via API.
2. The favorite list can be accessed via "My Favorites".
3. Favorite product can be removed from "My Favorites" list by clicking heart icon.
US08 | View items in the cart as a customer. | 1. Hover over cart icon displays "View Cart" link that navigates to the cart page. | High | Validate cart contents and modification actions with Selenium + API.
2. The cart page displays all selected products with their prices and total cost.
3. The customer can remove items from cart.
US09 | Confirm items in the cart as a customer. | 1. The customer can confirm the cart contents. | High | Validate cart summary and confirmation flow with Selenium + API.
2. Confirmation shows a summary of items and total price.
US10 | View the catalog of all products as a store manager. | 1. Store Manager can view the catalog of all products. | High | Validate view operations for products with Selenium + API.
US11 | Add a new product as a store manager. | 1. Store Manager can add a new product by filling in all required fields. | High | Validate product addition with required fields and success criteria. Validate the added product via API.
2. An error should appear for missing fields. (Name, Price, Stock, SKU)
3. An error should be displayed if SKU(stock code) is used that has already been taken.
3. Successfully added products should appear in the catalog.
US12 | Edit an existing product as a store manager. | 1. The manager can update any product details. | Medium | Validate edit functionality and catalog updates. Validate the updated product via API.
2. Changes reflect in the catalog after saving.
3. An error is shown for invalid or missing inputs.
US13 | Delete a product from the catalog as a store manager. | 1. Clicking delete prompts a confirmation dialog. | Medium | Validate delete confirmation and catalog updates. Validate the deleted product via API.
2. Confirming deletes the product, and it no longer appears in the catalog.
3. Confirming deletes diplays a success notification.
4. Canceling retains the product in the catalog.
US14 | View all users in the system as an Admin. | 1. Admin can view all users in the system. | High | Validate search functinality with Selenium + API.
2. Admin can search users by email.
3. If the entered email matches an existing user, that user’s details should be displayed
4. If no user is found with the entered email, show a message: "No user found"
US15 | Add a new user as an Admin. | 1. Admin can add a new user with valid inputs. | High | Validate new user addition and required field validation. Validate the added user via API.
2. Missing fields show an error. (Name, Role, Email, and Password)
3. Invalid email show a validation error message.(Please include an '@' in the email address.)
4. An error should be displayed if an email is used that has already been taken.
5. Successfully added users appear in the user list.
US16 | Edit existing user details as an Admin. | 1. The Admin can update Name, Role, Email, or Password. | Medium | Validate user edit functionality and list updates. Validate the updated user via API.
2. Changes reflect in the user list after saving.
3. An error appears for invalid or missing inputs.
US17 | Delete a user as an Admin. | 1. Clicking delete prompts a confirmation dialog. | Medium | Validate delete confirmation and list updates. Validate the deleted user via API.
2. Confirming removes the user, and they no longer appear in the list.
3. Canceling retains the user in the system.
US18 | View all stores in the system as an Admin. | 1. Admin can view all stores. | High | Validate view operations for stores with Selenium + API.
US19 | Add a new store as an Admin. | 1. Admin can add a new store with valid inputs. | High | Validate new store addition and required field validation. Validate the added store via API.
2. Missing fields show an error. (Name, Description, Location, Admins)
5. Successfully added stores appear in the stores list.
US20 | Edit existing store details as an Admin. | 1. The Admin can update Name, Description, Location and Admins. | Medium | Validate user edit functionality and list updates. Validate the updated store via API.
2. Changes reflect in the stores list after saving.
3. An error appears for invalid or missing inputs.
US21 | Delete a store as an Admin. | 1. Clicking delete prompts a confirmation dialog. | Medium | Validate delete confirmation and list updates. Validate the deleted store via API.
2. Confirming removes the store, and they no longer appear in the list.
3. Canceling retains the store in the system.

## Test Cases
User Story ID | Test Case ID | Test Objective | Pre-Condition | Steps | Test Data | Expected Result | Actual Result | Status
US01 | US01_TC001 | Verify successful account registration | User is on the registration page | 1. Enter "John" in the Name field. | Name: "John Doe", Email: "john@example.com", Password: "Password123" | User is registered successfully and redirected to the dashboard. | The system display http code "500-SERVER ERROR ", and not allow the user to Resgister | fail
2. Enter "john@example.com" in the Email field.
3. Enter a valid Password and Confirm Password.
4. Click the "Register" button.
US01 | US01_TC002 | Empty Name field | User is on the registration page | 1.Leave empty the Name fild | Email: "john@example.com", Password: "Password123" | The system should display an error message , and should not allow the user to Resgister | The system display an error message "The name field is required.", and not allow the user to Resgister | pass
2. Enter "john@example.com" in the Email field.
3. Enter a valid Password and Confirm Password.
4. Click the "Register" button.
US01 | US01_TC003 | Empty Email field | User is on the registration page | 1. Enter "John" in the Name field. | Name: "John Doe", Password: "Password123" | The system should display an error message , and should not allow the user to Resgister | The system display an error message "The email field is required.", and not allow the user to Resgister | pass
2.Leave empty Email field
3. Enter a valid Password and Confirm Password.
4. Click the "Register" button.
US01 | US01_TC004 | Empty password field | User is on the registration page | 1. Enter "John" in the Name field. | Name: "John", Email: "john@example.com" | The system should display an error message , and should not allow the user to Resgister | The system display an error message"The password field is required" , and not allow the user to Resgister | pass
2. Enter "john@example.com" in the Email field.
3.Leave empty password field
4. Click the "Register" button
US01 | US01_TC005 | Empty confirmation password field | User is on the registration page | 1. Enter "John" in the Name field. | Name: "John Doe", Email: "john@example.com", Password: "Password123" | The system should display an error message , and should not allow the user to Resgister | The system display an error message "The password field confirmation does not match" , and not allow the user to Resgister | pass
2. Enter "john@example.com" in the Email field.
3. Enter a valid Password 4.Leave empty Confirm Password.
4. Click the "Register" button
US01 | US01_TC006 | The Email is written in invalid format | User is on the registration page | 1. Enter "John" in the Name field. | Name: "John Doe", Email: "john.com@.com", Password: "Password123" | The system should display an error message , and should not allow the user to Resgister | The system display an error message "The email field must be a valid email address." , and not allow the user to Resgister | pass
2. Enter "john@example.com" in the Email field.
3. Enter a valid Password and Confirm Password.
4. Click the "Register" button
US01 | US01_TC007 | Name with special caracter | User is on the registration page | 1. Enter "John@" in the Name field. | Name: "John@ Doe", Email: "john@example.com", Password: "Password123" | The system should display an error message , and should not allow the user to Resgister | The system not display an error message , and allow the user to Resgister | fail
2. Enter "john@example.com" in the Email field.
3. Enter a valid Password and Confirm Password.
4. Click the "Register" button
US01 | US01_TC008 | Name with Number | User is on the registration page | 1. Enter "John1" in the Name field. | Name: "John1 Doe", Email: "john@example.com", Password: "Password123" | The system should display an error message , and should not allow the user to Resgister | The system not display an error message , and allow the user to Resgister | fail
2. Enter "john@example.com" in the Email field.
3. Enter a valid Password and Confirm Password.
4. Click the "Register" button.
US01 | US01_TC009 | Password less than 6 charcters | User is on the registration page | 1. Enter "John" in the Name field. | Name: "John Doe", Email: "john@example.com", Password: "Passw" | The system should display an error message , and should not allow the user to Resgister | The system display an error message "The password field must be at least 6 characters" , and not allow the user to Resgister | pass
2. Enter "john@example.com" in the Email field.
3.Enter password with at least 5 characters and confirm the password
4. Click the "Register" button.
US01 | US01_TC010 | Password and confirm password do not match | User is on the registration page | 1. Enter "John" in the Name field. | Name: "John Doe", Email: "john@example.com", Password: "Password123", confirmation password "Paass123" | The system should display an error message , and should not allow the user to Resgister | The system display an error message "The password confirmation does not match" , and not allow the user to Resgister | pass
2. Enter "john@example.com" in the Email field.
3.Enter password dose not match the confirm password
4. Click the "Register" button.
US01 | US01_TC011 | verification of successful account creation | The user must not have an existing account with the same email | 1.navigate to the registration page" 2.Enter valid (Name ,Email, Password,Confirm password)" 3.Click on the register button | Name: "John Doe", Email: "john@example.com", Password: "Password123" | The system display confirmation message such as " Account created successfully" and redirects the user to the dashboard page | The system display http code "500-SERVER ERROR ", and not allow the user to Resgister | fail
US02 | US02_TC001 | The user Login using a valid Email and Password | user should be on the log in page | 1.Enter the valid Email in the Email field | Email: "customer@sda.com", Password: "Password123" | The system should authenticate the user and redirect them to the dashboard
2. Enter a valid password
3.click the "Log in" button
US02 | US02_TC002 | The user Login using incorrect Password | user should be on the log in page | 1.Enter the valid Email in the Email field | Email: "customer@sda.com", Password: "word123" | The system should display an error message , and should not allow the user to Log in
2. Enter incorrect password
3.click the "Log in" button
US02 | US02_TC003 | The user Login using invalid Email format | user should be on the log in page | 1. Enter invalid Email format. | Email: "custome.com@com", Password: "Password123" | The system should display an error message and should not allow the user to Log in
2.Enter "Password123" in password field
3.click the "Log in" button
US02 | US02_TC004 | Empty Email field | user should be on the log in page | 1.Leave empty the Email field | Password: "Password123" | The system should display an error message and should not allow the user to Log in
2.Enter "Password123" in password field
3.click the "Log in" button
US02 | US02_TC005 | Empty Password field | user should be on the log in page | 1.Enter the valid Email in the Email field | Email: "cutomer.com@com" | The system should display an error message and should not allow the user to Log in
2.Leave empty the Password field
3.click the "Log in" button
US02 | US02_TC006 | The system should log in successfully and redirect the user to the dashboard page | user should be on the log in page | 1.Enter the valid Email in the Email field | Email: "john.com@com", Password: "Password123" | The system should securely log out the user and redirect them to the log in page
2.Enter the valid Password in the Password field
US03 | US03_TC001 | click "Log Out" | the user in prouducts page | 1.Move the crusor over the person icon |  | The "Log Out" is clicked successfully | The "Log Out" is clicked successfully | pass
2.Click on "Log out"
US03 | US03_TC002 | Verify user is redirected to log in page after log out | the user in prouducts page | 1.Move the crusor over the person icon |  | The user is successfully logged out and the system redirects the user to the log in page | The user is successfully logged out and the system redirects the user to the log in page | pass
2.Click on "Log out"
US03 | US03_TC003 | Verify the user session is end securely | the user in prouducts page | 1.Move the crusor over the person icon 2.Click on "Log out" |  | The system should prevent access to any restricted page after log out , the session should be invalidated , and the user should remain on or be redirected to the log in page | The system should prevent access to any restricted page after log out , the session should be invalidated , and the user should remain on or be redirected to the log in page | pass
US04 | US04_TC001 | Verify customer Login successful | Customer login | 1. Browser opend | Email: "customer@sda.com" Password: "Password.12345" | customer login successfully redirected to the Home Customer page . | customer login successfully redirected to the Home Customer page . | pass
2. login
3. Negative to url /Customer
US04
US04 | US04_TC002 | Verify Cusromer can see products | Customer is on customer page | Observe each product card | \ | All products are visible | All products are visible | pass
US04 | US04_TC003 | Verify products load quickly with dateils | Customer is on customer page | 1. Wait for products to load | \ | All products are loaded < 3s , and visible with name, price , image and Desctiption . Data matches GET API response. | All products are loaded < 3s , and visible with name, price , image and Desctiption . | pass
2. show Name
3. show Price
4. show Images
5. show Description
US05 | US05_TC001 | Verify checking details all required information of one product. | Customer is on customer page | 1. Click on any product to open its detail page. | Any prodect card | Product detail page show correctly. Data matches API response.
2. Verify the product name is displayed.
3. Verify the product price is displayed.
4. Verify the product description is displayed.
5. Verify the product image is displayed.
US06 | US06_TC001 | Verify adding a product to the car | User is logged in and browsing the products page | 1. Choose a product on the page. | Cart contains: “Classic Toy Car” | User is added item successfully and product appears in the cart. | Product “Classic Toy Car” appeared correctly in the cart with details. | pass
2. Click the Add to Cart button.
3. Open the cart page
US06 | US06_TC002 | Verify removing an item from the cart | User has added at least one product to the cart | 1.Open the cart page. | Cart contains: “Classic Toy Car” | The selected product is removed from the cart, and a message "Product removed successfully" is displayed. | Product was removed successfully,the message appeared. | pass
2.Locate the product to be removed.
3.Click the Remove button next to the product.
US07 | US07_TC001 | Verify Cusromer can Mark products as favorites | Customer is on customer page | Click the heart icon on a product to mark it as favorite. | Any prodect card | Proudact is added to favorites Heart icon Change favorite status. | Proudact is added to favorites Heart icon Change favorite status. | pass
US07 | US07_TC002 | Verify erorr message apear if Cusromer Mark same products as favorites again | Customer has a product favorite on customer page | 1. Click the heart icon on a product to mark it as favorite. | Any favorite prodect card | message erorr apear successfully | message erorr apear successfully | pass
2. massage "Product is already in favorites."
US07 | US07_TC003 | Verify accessing favorite list | Customer has at least one product favorite | 1. Negative to My Favorites page | All favorite prodect card | All products are visible successfully Data matches API response. | All products are visible successfully | pass
2. all favorited products appear
US07 | US07_TC004 | Verify removing prudact from favorite | Customer has a product favorite on customer page | 1. click Heart icon on a favorite product | Any favorite prodect card | remove producat from favorites and updates Heart icon status in home page successfully | remove producat and updates Heart icon status successfully
|  |  |  | 2. product should removed |  |  |  | pass
3.chack the prodect has removed in home page
US07 | US07_TC005 | Verify adding product to favorites | Product exists | Send POST request to /favorites with product id. | Any id prodect card product ID: 210 | Response code 200 and Product added successfully
pass
US7 | US07_TC006 | Verify retrieving favorite list | At least one favorite exists | Send GET request to /favorites | All favorite prodect card | Response code 200 and only added product show
pass
US7 | US07_TC007 | Verify removing favorite | Product already favorited | Send DELETE request to /favorites/{id} | Any id prodect card product ID: 210 | Response code 200 and Product removed successfully.
US07
pass
US08 | US08_TC001 | Verify that the cart displays added items | User has added product to the cart | 1. Click on the View Cart button. | Product Name: "Classic Toy Car " | All added products are displayed with correct details (name, price) | Cart displayed both products correctly with accurate name, price.
|  |  |  | 2. View the list of added products. |  |  |  | pass
US09 | US09_TC001 | Verify cart confirmation process | User is on User is on the cart page with products added registration page | 1. Review the cart items.. | Cart contains: “Classic Toy Car” | User is redirected to the checkout page and cart confirmation is successful. | Success message displayed correctly and order was saved. | pass
2. Click the Confirm Cart button.
3. A success message is displayed.
US10 | US10_TC001 | Validate View the catalog of all products as a store manager successfully | Store Manger is on the Login page | 1. Enter "storemanager@sda.com" in email field | "Email: ""storemanager@sda.com"", Password: ""Password.12345""" | Manger should be navigated to manger Dashboard | Manger should be navigated to manger Dashboard | pass
2. Enter "Password.12345" in password field
3. Click on Login in button
US11_01 | US10_TC001 | Validate Add a new product as a store manager successfully | Manger is on the Product catalog page | 1.Click on the add product button | 1.Product Name "Headphones" 2.Product Price "300" 3.Product Stock "180" 4.Product SKU "390490" | Manger should be able to Add new Product | Product Created Successfully is displayed | pass
2.Enter Product Name
3.Enter Product Price
4.Enter Product Stock
5.Enter Product SKU
US11_02 | US10_TC002 | Empty Product name input | Manger is on the Product catalog page | 1.Click on the add product button | 1.Product Price "100" 2.Product Stock "50" 3.Product SKU "123456" | Manger should be able see 'The name field is required' error message | `The name field is required`" error message is displayed | pass
2.Leave Empty Product Name
3.Enter Product Price
4.Enter Product Stock
5.Enter Product SKU
US11_03 | US11_TC003 | Empty Product price input | Manger is on the Product catalog page | 1.Click on the add product button | 1.Product Name "Phone" 2.Product Stock "100" 3.Product SKU "123456" | Manger should be able see 'The price field is required' error message | `The price field is required` error message is displayed | pass
2.Enter Product Name
3.Leave Empty Product Price
4.Enter Product Stock
5.Enter Product SKU
US11_04 | US11_TC004 | Empty product Stock input | Manger is on the Product catalog page | 1.Click on the add product button | 1.Product Name "Camera" 2.Product Price "1400" 3.Product SKU "123456" | Manger should be able see 'The stock field is required' error message | `The stock field is required' error message is displayed | pass
2.Enter Product Name
3.Enter Product Price
4.Leave Empty Product Stock
5.Enter Product SKU
US11_05 | US11_TC005 | Empty Product SKU input | Manger is on the Product catalog page | 1.Click on the add product button | 1.Product Name "Phone" 2.Product Price "2500" 3.Product Stock "250" | Manger should be able see 'The sku field is required' error message | `The sku field is required` error message is displayed | pass
2.Enter Product Name
3.Enter Product Price
4.Enter Product Stock
5.Leave Empty Product SKU
US11_06 | US11_TC006 | SKU(stock code) is used that has already been taken. | Manger is on the Product catalog page | 1.Click on the add product button | 1.Product Name "Camera" 2.Product Price "1900" 3.Product Stock "100" 4.Product SKU "397497" | Manger should be able see The sku has already been taken' error message | `The sku has already been taken` error message is displayed | pass
2.Enter Product Name
3.Enter Product Price
4.Enter Product Stock
5.Enter Duplicated/Used Product SKU
US12 | US10_TC001 | Edit an existing product as a store manager(Happy Path) | Manger is on the Product catalog page | 1.Click on the Edit button beside Headphones | 1.Price "700" 2.Stock "200" 3.Discount "20.0" | Manger should be able to see the 'Product updated successfully' message | the new modified Product displayed | pass
2.change the price to 700
3.change the stock to 200
4.add a discount of %20
US12 | US10_TC002 | Edit an existing product as a store manager (delete name) | Manger is on the Product catalog page | 1.Click on the Edit button beside Headphones | 1.Name "Headphones" | Manger should be able see 'The name field is required' error message | `The name field is required`" error message is displayed | pass
2.Delete Name
3.Click submit
US12 | US10_TC003 | Edit an existing product as a store manager (delete price) | Manger is on the Product catalog page | 1.Click on the Edit button beside Headphones | 1.Price "700" | Manger should be able see 'The price field is required' error message | `The price field is required` error message is displayed | pass
2.Delete Price
3.Click submit
US12 | US10_TC004 | Edit an existing product as a store manager (delete stock) | Manger is on the Product catalog page | 1.Click on the Edit button beside Headphones | 1.Stock "200" | Manger should be able see 'The stock field is required' error message | `The stock field is required' error message is displayed | pass
2.Delete Stock
3.Click submit
US12 | US10_TC005 | Edit an existing product as a store manager (delete SKU) | Manger is on the Product catalog page | 1.Click on the Edit button beside Headphones | 1.SKU "390490" | Manger should be able see 'The sku field is required' error message | `The sku field is required` error message is displayed | pass
2.Delete SKU
3.Click submit
US13_01 | US10_TC001 | Delete a product from the catalog as a store manager successfully | Manger is on the Product catalog page | 1.Click on the Delete button beside Laptop | 1.Name "Headphones" | Manger should be able to delete product successfully | Product Deleted Successfully!' massage dispalyed | pass
2.Click on Yes, delete it!
US13_02 | US10_TC002 | Cancel Delete a product from the catalog as a store manager successfully | Manger is on the Product catalog page | 1.Click on the Delete button beside Laptop | Manger should be able to see the Product in the Products page | Manger should be able to see the Product in the Products page | The product named "Headphones" is still available | pass
2.Click on Cancel
US14 | US14_TC001 | Verify that Admin can view all users in the system | Admin is logged in | 1. Log in as Admin | Email: admin@sda.com | A list of all registered users is displayed with correct details
|  |  |  | 2. Navigate to "Users" page | Password: 12345
3. Observe the list of users displayed
US14 | US14_TC002 | Verify that Admin can search users by email | Admin is logged in and users exist | 1. Go to “Users” page | Existing user email | The user with the entered email appears in the results
2. Enter known user email in search bar
3. Click “Search”
US14 | US14_TC003 | Verify that invalid search shows "No user found" message | Admin is logged in | 1. Enter non-existing email in search box | test@invalid.com | Message “No user found” is displayed
2. Click “Search”
US15 | US15_TC001 | Verify adding a new user with valid data | Admin is logged in | 1. Click “Add User” | Name: “Sarah Test” | User added successfully and appears in the list
|  |  |  | 2. Enter Name, Role, Email, and Password | Email: sarah@test.com
|  |  |  | 3. Click “Save” | Role: Customer , Password: Test123
US15 | US15_TC002 | Verify missing field validation | Admin is logged in | 1. Click “Add User” | Missing Email | Validation error “Email is required” appears
2. Leave “Email” empty
3. Click “Save”
US15 | US15_TC003 | Verify invalid email format validation | Admin is logged in | 1. Enter “sarah_test.com” in Email field | Invalid Email | Validation message “Enter a valid email address” appears
2. Click “Save”
US16 | US16_TC001 | Verify editing user details | Admin is logged in and user exists | 1. Go to “Users” list | Name: “Updated User” | User details updated successfully
2. Click “Edit” on an existing user
3. Modify user name and click “Save"
US16 | US16_TC002 | Verify validation error for missing inputs during edit | Admin is logged in | 1. Click “Edit” on an existing user | Missing Email | Error “Email is required” displayed"
2. Remove Email field content
3. Click “Save"
US17 | US17_TC001 | Verify deleting user from list | Admin is logged in and user exists | 1. Go to “Users” list | Any existing user | User deleted successfully and removed from list
2. Click “Delete” next to user
3. Confirm deletion
US17 | US17_TC002 | Verify canceling delete action | Admin is logged in | 1. Click “Delete” on a user | Any existing user | User remains in list
2. Click “Cancel”
US18 | US18_TC001 | Verify Admin can view all stores list | Admin is logged in and on the Stores page | 1.Navigate to “Stores” page 2. Observe the list of stores displayed. | — | All existing stores are displayed correctly with Name, Description, Location, and Admins.
US18 | US18_TC002 | Validate store list data via API | Admin has valid API credentials | 1.Send a GET request to /stores endpoint 2. Compare API response with UI list. | — | API response matches UI data (same number of stores and same details).
US19 | US19_TC001 | Verify adding a new store with valid data | Admin is logged in and on the Add Store page | 1.Click “Add New Store” 2. Enter valid Name, Description, Location, and Admins 3. Click “Save”. | Name: 'Extra', Description: 'Electronics store', Location: 'Riyadh', Admins: 'admin@test.com' | Store is added successfully and visible in the store list
US19 | US19_TC002 | Verify error message for missing required fields | Admin is logged in and on Add Store page | 1. Leave one or more required fields empty 2. Click “Save”. | Missing Name or Location | Error message is shown for missing required fields; store is not added.
US19 | US19_TC003 | Verify added store appears in API | Admin successfully added a store previously | 1. Refresh the store list page 2. Send a GET request to /stores endpoint. | — | Newly added store appears in API response.
US20 | US20_TC001 | Verify successful update of store details | Admin is logged in and a store exists in the list | 1. Click “Edit” for an existing store 2. Modify Name, Description, or Location 3. Click “Save”. | Name: 'Updated Store', Location: 'Jeddah' | Store details update successfully; confirmation message shown; updated data visible in UI.
US20 | US20_TC002 | Verify successful update of store details via API | Admin has a valid authentication token and an existing store ID available | Send PUT request to /stores/{storeId} endpoint with updated Name, Description, and Location in JSON body. | Name: 'Updated Store', Description: 'Updated desc', Location: 'Jeddah' | Response status code is 200; response body contains updated store details matching the request; changes are reflected when fetching the store via GET /stores/{storeId}.
US20 | US20_TC003 | Verify error for missing/invalid inputs during edit | Admin is logged in and editing a store | 1. Clear one or more required fields 2. Click “Save”. | Empty Name field | Error message shown; changes are not saved.
US20 | US20_TC004 | Verify updated store data is reflected in the list after update via API | Admin has successfully updated a store via PUT /stores/{storeId} endpoint | Send GET request to /stores endpoint and verify the updated store details in the response. | Store ID used in previous update test | Updated store details (Name, Description, Location) are correctly reflected in the GET /stores response.
US20 | US20_TC005 | Verify updated data reflects in the list after saving | Admin updated a store successfully | 1. Go back to the store list 2. Check the updated store. | — | Updated details are displayed in UI
US21 | US21_TC001 | Verify delete confirmation dialog appears | Admin is logged in and on the store list page | 1. Click “Delete” on a store 2. Observe the confirmation dialog. | — | Confirmation dialog appears asking for confirmation.
US21 | US21_TC002 | Verify store can be deleted successfully via API | Admin has a valid authentication token and an existing store ID | Send DELETE request to /stores/{storeId} endpoint. | Store ID of an existing store | Response status code is 200 or 204; response body confirms deletion; store no longer appears in GET /stores list.
US21 | US21_TC003 | Verify store is deleted after confirming deletion | Admin is logged in and confirmation dialog appears | 1. Click “Delete” on a store 2. Confirm deletion . | — | Store is removed from UI list; success message shown.
US21 | US21_TC004 | Verify store is deleted and no longer appears in the list via API | Admin has a valid authentication token and an existing store ID | Send DELETE request to /stores/{storeId} endpoint, then send GET request to /stores endpoint to verify deletion. | Store ID of the deleted store | Response status code is 200 or 204; store is no longer present in the GET /stores response list.
US21 | US21_TC005 | Verify canceling deletion keeps the store intact | Admin is logged in and confirmation dialog appears | 1. Click “Delete” on a store 2. Click “Cancel” in confirmation dialog. | — | Store remains in the list; no changes occur in system.

## Schedule
Week 1 | Thursday | Sunday | Monday | Tuesday | Wednesday
30-10-25 | Grooming Meeting (Sprint 1) Project Introduction US Pointing Assigning US Sprint Planning Meeting | Jira Session |  | Daily Meeting | GitHub Collabaration Daily Meeting
|  | Open jira account Creating a project Add team members | Daily Meeting | WritingTest Case in Excel
|  | Entering US into the product backlog | WritingTest Case in Excel | Transferring Test Cases to Jira Run Test Cases Manually | Creating Cucumber framework
Creating GitHub Repo
Week 2 | Thursday | Sunday | Monday | Tuesday | Wednesday
2025-11-06 | Test Coding | Test Coding | Test Coding | Sprint Review | Grooming Meeting
| Daily Meeting | Daily Meeting | Daily Meeting |  | API Sprint Planning Meeting
| Test Coding | Test Coding | Test Coding |  | Writing Test Cases in Excel Performing API Tests in Postman
| Execution of code | Execution of code | Execution of code
Week 3 | Thursday | Sunday | Monday | Tuesday | Wednesday
2025-11-13 | Transferring Test Cases to Jira | Coding API Tests | Coding API Tests | Execution of code- Github Conflict Resolution | Demo Meeting
| Daily Meeting | Daily Meeting | Daily Meeting | Daily Meeting
| Creating API TestNG Framework | Coding API Tests | Coding API Tests
Preparation For Demo Meeting

## Sprint Planning
| US points | [5 empty] | Average | Who?
| person 1 | person 2 | person 3 | person 4 | person 5 | person 6
US01 | 2
US02 | 2
US03 | 1
US04 | 2
US05 | 2
US06 | 2
US07 | 1
US08 | 2
US09 | 4
US10 | 2
US11 | 4
US12 | 3
US13 | 2
US14 | 3
US15 | 3
US16 | 3
US17 | 2
US18 | 2
US19 | 2
US20 | 3
US21 | 2